## Gantt
꙳der Chef bakery Previous activities
|  |  |  | September |  | October |  |  |  |  | November |  |  |  | December
| Week Activities | Responsable | Check up | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
A | Project proposal | All
B | Project generals | Hiram
C | Justify | Hiram
D | Feasibility analysis | Cris
E | Canvas Model | Cris
F | Organizational structure | Hiram
G | Budget Check | Alex
H | Pilot test | Cris
I | Supplement assingnment | All
J | Operations diagram | Cris
K | Making times 1 | Cris
L | Lay out proposal | Salvador
M | Set standarization | All
N | Making times 2 | All
O | Invest work | Alex
P | Adjust work time | All
Q | Resulst explotation planning | Salvador
R | Making times 3 | All
S | Work check up | Salvador
T | Making presentation | Alex
U | Project presentation | All
|  |  |  | September |  | October |  |  |  |  | November |  |  |  | December
| Week Activities | Responsable | Check up | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
| Project proposal | All
| Project generals | Hiram
| Justify | Hiram
| Feasibility analysis | Cris
| Canvas Model | Cris
| Organizational structure | Hiram
| Budget Check | Alex
| Pilot test | Cris
| Supplement assingnment | All
| Operations diagram | Cris
| Making times 1 | Cris
| Lay out proposal | Salvador
| Set standarization | All
| Making times 2 | All
| Invest work | Alex
| Adjust work time | All
| Resulst explotation planning | Salvador
| Making times 3 | All
| Work check up | Salvador
| Making presentation | Alex
| Project presentation | All

## CPM
| Activities | Time | Precedence
A | Project proposal | 1 | -
B | Project generals | 1 | A
C | Justify | 1 | B
D | Feasibility analysis | 1 | B
E | Canvas Model | 1 | B | [7 empty] | 2 | C | 3
F | Organizational structure | 1 | A | [7 empty] | 8 | 1 | 9
G | Budget Check | 1 | A
H | Pilot test | 1 | A
I | Supplement assingnment | 1 | H | START | 0 | A | 1 | 1 | B | 2 | 2 | D | 3
J | Operations diagram | 2 | H | 0 | 0 | 1 | 1 | 7 | 1 | 8 | 8 | 1 | 9
K | Making times 1 | 1 | J,I
L | Lay out proposal | 1 | K
M | Set standarization | 4 | L | [7 empty] | 2 | E | 3
N | Making times 2 | 1 | M | [7 empty] | 8 | 1 | 9
O | Invest work | 1 | N | [13 empty] | 4 | L | 5
P | Adjust work time | 1 | O | [13 empty] | 8 | 1 | 9
Q | Resulst explotation planning | 1 | G |  |  |  |  | 1 | H | 2 | 2 | I | 3
R | Making times 3 | 1 | P |  |  |  |  | 1 | 1 | 2 | 2 | 1 | 3
S | Work check up | 1 | R | [10 empty] | 3 | K | 4 | 4 | M | 5
T | Making presentation | 1 | S | [10 empty] | 3 | 1 | 4 | 8 | 1 | 9
U | Project presentation | 1 | T | [7 empty] | 2 | J | 3 | [6 empty] | 5 | O | 6
[11 empty] | 2 | 1 | 3 | [6 empty] | 8 | 1 | 9
[17 empty] | 4 | N | 5
[17 empty] | 4 | 1 | 5
[20 empty] | 5 | P | 6 | 6 | R | 7 | 7 | S | 8 | 8 | T | 9 | 9 | U | 10 | END
[20 empty] | 5 | 1 | 6 | 6 | 1 | 7 | 7 | 1 | 8 | 8 | 1 | 9 | 9 | 1 | 10 | 10
[8 empty] | 1 | G | 2 | 2 | Q | 3
[8 empty] | 7 | 1 | 8 | 8 | 1 | 9
[8 empty] | 1 | F | 2
[8 empty] | 8 | 1 | 9